## Sheet1
Requirements Test
Requirement | Expected | Actual | Pass or Fail
Login or Sign Up | User will have the option to login or sign up on the landing page | User only sign in option | Fail
Login or Sign Up | User will have the option to login or sign up on the landing page | User sees option to sign up and sign in | Pass
Hide Password Field | Password text should be replaced by bullet points | Password field shows plain text | Fail
Hide Password Field | Password text should be replaced by bullet points | Password is replaced by bullet points | Pass
Display Online Users | After logged in, display a list of the username at top | No username is shown | Fail
Display Online Users | After logged in, display a list of the username at top | Username is shown followed by "is online" | Pass
Text Field | User will see a text field and a button to send message | Text field is shown with button saying "Send Message" | Pass
Display Message Sent | Display contents of message after "Send Message" is clicked | Message text is displayed | Pass
Display Username of Message Sender | Each message sent should contain by the username of the sender of that message | Message is sent but name of user is not shown | Fail
Display Username of Message Sender | Each message sent should contain the username of the sender of that message | Username of message sender is shown after the message text | Pass
Display Message Timestamp | Display the timestamp from when each message was sent | Message is shown but not the timestamp | Fail
Display Message Timestamp | Display the timestamp from when each message was sent | Timestamp is shown after the username of the message | Pass
Real Time Message Loading | After each message is sent, it should be loaded onto each user's feed automatically | User must refresh to see received messages | Fail
User Log Out | User should see a logout button on the chat page | Logout button visible | Pass
Successful Sign Up | User signs up successfully using email, username, password | DB is not updated | Fail
Successful Sign Up | User signs up successfully using email, username, password | DB contains user details | Pass
Successful Login | User who has an account will be directed to the chat after entering user details | Login was successful | Pass
Successfjul Logout | User will be logged out completely after clicking logout button | Logout was successful | Pass